## Slide 1: WP7. Pilot coordination and continuous risk assessment
Michał Zimniewicz
Poznan Supercomputing and Networking Center
Up2U Update Webinar 20th December 2018

## Slide 2: Pilot Progress
Country | CPD Module 1 | Numbers of schools / teachers | Pilots (CPD Module 2) | Targeted schools
Germany | Q2 2019 |  | Q2 2019 | Private teachers
Greece | Mar – May 2018 | 8 / 80 | Jan – Feb 2019 | 8
Hungary | Aug – Sep 2018 | 8 / 12 | Early 2019 | 8
Italy | Apr – May 2018 | 5 / 11 | Feb – May 2019 | 
Lithuania | Nov – Dec 2018 | 10 / 15 | Nov – ongoing | 76
Poland | Jun – Oct 2018 | 15 / 30 | Jan – March 2019 | 15
Portugal | Fall 2018, Jan 2019 | 1 school, more in 2019 | 2019 | 
Spain | Nov – Dec 2018 | 7 / 7 | 2019 | 
CERN | --- | --- | Ongoing, no updates | 1 class
Notes: CPD trainings have already started in most of the pilot countries.
Pilots involving students are scheduled in most cases.
Concrete actions for reaching new schools are scheduled in particular pilot countries and reported in D7.3.
Detailed monthly pilot updates are submitted to EC – first in November, another one just now.

## Slide 3: D7.3: Report on the large-scale pilot services, essential features and their improvements
Led by KTU.
Finalised. To be submitted to GEANT today.
The scope:
  Updates on pilot countries and their plans
  Updates on pilot infrastructures
  First MVP suggestions and first improvements
  Risk management update
  Project and pilot evaluation

## Slide 4: Future MVP Improvements
Dec 2018
  Application Toolbox v.2.0
  1st set of improvements implemented
  D7.3 reports on the improvements
Q1-Q2 2019
  Collecting new suggestions from students ASAP
  Some improvements to be reported at the project review in spring
  D4.3 to report on 2nd set of improvements
Q3-Q4 2019
  Collecting new suggestions, implementing improvements
  D7.4 to report on 3rd set of improvements