## Slide 1: WP7. Pilot coordination and continuous risk assessment
Michał Zimniewicz
Poznan Supercomputing and Networking Center
Up2U Update Webinar 24th January 2019

## Slide 2: D7.3: Report on the large-scale pilot services, essential features and their improvements
Led by KTU
Submitted to EC in early January

## Slide 3: Pilot Progress
Country | CPD Module 1 | Numbers of schools / teachers in CPD1 | Pilots (CPD Module 2) | Schools targeted now or soon
Germany | Q2 2019 |  | Q2 2019 | Private teachers
Greece | Mar – May 2018 | 8 / 80 | Jan – Feb 2019 | 8
Hungary | Aug – Sep 2018 | 8 / 12 | Early 2019 | 8 now, 40 soon
Italy | Apr – May 2018 | 5 / 11 | Mar – May 2019 | 
Lithuania | Nov – Dec 2018 Feb 2019 | 10 / 15 - / 160 | Nov 2018 – ongoing | 20-80
Poland | Jun – Oct 2018 | 15 / 30 | Feb – March 2019 | 15
Portugal | Jan 2019 | 1 school+ | 2019 | 
Spain | Nov – Dec 2018 | 7 / 7 | 2019 | 
Notes: CPD trainings have already started all pilot countries.
Pilots involving students are lauched in Lithuania and are about to start in most of other countries.
Concrete actions for reaching new schools are scheduled in all pilot countries.
Detailed monthly updates about pilots are submitted to EC starting from November.

## Slide 4: Minimum Viable Product
Q1-Q2 2019 – The second phase for collecting MVP suggestions
  Collecting new suggestions from students in pilots, mainly via Google Form
  Some improvements to be reported at the project review in spring
  More improvements to be reported in June

## Slide 5: Quality Assurance
Testing activities recently launched for:
  The upgrades of Moodle
  Poddium (PR) now available as standalone tool
  EduOER Android App