## Slide 1: Up2U monthly webinar 24/01/19 WP5 [final]
Stefano Lariccia
UROMA

## Slide 2
[Continued from previous month] Contribution to D7.3 and D8.3
Started organizing WP5 Sub-group organization
Started organizing D5.4 under TAU monitoring
Pilots planning Preparation of Learning Units
Learning Units preparation (continues from 11/18)
  Unit 1: (to be translated and uploaded onto the Up2U learning system)
  Unit 2: (to be translated and uploaded onto the Up2U learning system)
  Unit 3: Language analysis and Critical Thinking. How to increase you ability to produce texts and video clips (in progress, will be completed by the end of the month)
MONTH 24, December 2018

## Slide 3
SMC planning for supporting Pilot activities
Supporting and counseling over Pilots from a pedagogical point of view
  Greek Pilot
  Italian Pilot
  Lithuanian Pilot
  Portuguese Pilot
  Spanish Pilot
Started writing D5.4 under TAU monitoring
Monitoring Task 5.4
RIGHT NOW, MONTH 25 January 2019

## Slide 4
Monitoring Task 5.4
Providing models to collect and analyse data
  Progressing activities on evaluation models based on data collection; exploring LRS query methods and potential
  Implementing Learning Units based on Jupyter Notebooks. A Learning Path on Shakespeare is accessible now thorugh CS on Up2U; some others are in progress; a selection from Calysto is under way
RIGHT NOW, MONTH 25 January 2019 [2]

## Slide 5
Further piloting activities into Up2U ecosystem
  “Light” integration of existing Jupyter notebooks based on CommonSpaces integrated for formal/informal in Up2U;
  University as a Hub is planning first “flipped” class for Italian secondary schools based on CommonSpaces. 1 Pilot will start i classroom on February
  Starting planning May Meeting in Rome at SLERD 2019
  In Italy (to be integrated into WP7): started negotiation with Heritage Ministry to co-authoring a pilot in italian secondary schools about “Emergency and seismic education and risk mitigation” and “Valorisation of Archaeological sites” ; this latter activity will converge during SLERD 2019 in a demonstration of Up2U system used in Heritage studies.
RIGHT NOW, MONTH 25 January 2019 [3]