## Slide 1: Up2U monthly webinar 26/02/19 WP5 [draft]
Eli Shmueli, IUCC; Stefano Lariccia UROMA

## Slide 2
[from previous month] Finalising contribution to D7.3 and D8.3
Set up of WP5 Sub-group organization
Finalising D5.4 under IUCC supervision
Pilots planning: finalising preparation of Learning Units
Learning Units preparation (continues from 01/19)
  Unit 1: (to be translated and uploaded onto the Up2U learning system)
  Unit 2: (to be translated and uploaded onto the Up2U learning system)
  Unit 3: Language analysis and Critical Thinking. How to increase your ability to understand texts and documents (in progress, will be uploaded by the end of the month)
MONTH 26, January 2019

## Slide 3
Mentoring Pilot organization: Italy
  CYC2 Module 1: 1-2 weeks; CYC2 Module 2: 12 weeks, Online
  Distribution of Learning Path 1, 2 and 3 (the last 2 need to be translated)
  Schools engagement: GARR mailing the schools, and regional districts
Supporting Pilot organization: Greece
  Schools mailing: expected engagement of 100 schools
  Modeling a common collection of data
Supporting Pilot organization: Lithuania
  Schools engagement: active engagement of 80 schools
  Modeling a common collection of data
Supporting Pilot organization: Hungary
MONTH 26, January 2019

## Slide 4
Supporting Pilots, general overview:
  Supporting Pilot organization: Poland
    Schools mailing: expected engagement of 100 schools
    Modeling a common collection of data
  Supporting Pilot organization: Portugal
    Schools mailing: expected engagement of 30 schools
  Supporting Pilot organization: Spain
    Schools mailing: expected engagement of 30 schools
  Supporting Pilot organization: Switzerland
    Schools recruitment: expected engagement of 5 schools?
MONTH 26, January 2019

## Slide 5
[cont.] Supporting and counseling over Pilots from a pedagogical point of view
  Greek Pilot
  Italian Pilot
  Lithuanian Pilot
  Portuguese Pilot
  Spanish Pilot
Writing Deliverable 5.4 under IUCC supervision
  Collecting experiences from Pilot Countries
  Unifying the framework of Pilots
  Extending discussions about “Lesson Learnt” and “Local practices” to all the involved teams
  Preparing Surveys and other assessment tools
RIGHT NOW, MONTH 27, February 2019 [1]

## Slide 6
Task 5.4
  Starting activities about 3D exploration and AR and Interactive Learning Objects
Reporting into D5.4:
  How to provide models to collect and analyse data
  Progressing activities on evaluation models based on data collection; exploring LRS query methods and potential
  Redefining formal <-> informal learning relations, within and beside classroom
  Implementing Learning Units based on Jupyter Notebooks. Exploring other Notebook collections about Language, Heritage, Coding
RIGHT NOW, MONTH 27, February 2019 [2]

## Slide 7
Further piloting activities into Up2U ecosystem
  “Light” integration of existing Jupyter notebooks based on CommonSpaces integrated for formal/informal in Up2U;
  University as a Hub is planning first “flipped” class for Italian secondary schools based on CommonSpaces. 1 Pilot will start i classroom on February
  Starting planning May Meeting in Rome at SLERD 2019
  In Italy (to be integrated into WP7): started negotiation with Heritage Ministry to co-authoring a pilot in italian secondary schools about “Emergency and seismic education and risk mitigation” and “Valorisation of Archaeological sites” ; this latter activity will converge during SLERD 2019 in a demonstration of Up2U system used in Heritage studies.
RIGHT NOW, MONTH 25 January 2019 [3]

## Slide 8
Starting pilot activities. Up2U ecosystem into the classroom
  Pedagogical monitor to the Pilot in Italy
  Pedagogical monitor to Pilot in Greece
  Pedagogical monitor to the Pilot in Lithuania
  Pedagogical monitor to the Pilot in Poland
  Pedagogical monitor to the Pilot in Hungary
  Pedagogical monitor to the Pilot in Switzerland
  Pedagogical monitor to the Pilot in Spain
NEXT STEPS, MONTH 28 March 2019 [1]
Defining a possible common path to carry out the Pilot (e.g. goals, main contents and methodologies)
Providing partners with Learning Objects for teachers’ training (ENG or Sub Eng) about: technology enhanced learning, computational thinking, LALT
Establishing an evaluation protocol to assess participation and learning outcomes: (flexible) criteria to be followed, online survey, (optional) observational greed

## Slide 9
Further piloting activities into Up2U ecosystem
  Proceeding on “Light” integration of existing Jupyter notebooks based on CommonSpaces integrated for formal/informal in Up2U;
  UaH is planning first “flipped” class for Italian secondary schools based on CommonSpaces. 1 Pilot will start in classroom on February / March
  Proceeding on planning May Meeting in Rome at SLERD 2019
  Proceeding on [In Italy] (to be integrated into WP7): negotiation with Heritage Ministry to co-authoring a pilot in italian secondary schools about “Emergency and seismic education and risk mitigation” and “Valorisation of Archaeological sites” ; this will converge during SLERD 2019 in a demo of Up2U system used in Heritage studies. .
NEXT STEPS, MONTH 28 March 2019 [2]