## Slide 1: WP7. Pilot coordination and continuous risk assessment
Michał Zimniewicz
Poznan Supercomputing and Networking Center
Up2U Update Webinar 26th February 2019

## Slide 2: Detailed Milestones
Feb
Engaging students in Greece and Spain
New MVP feedback
Mar
Engaging students in Hungary, Italy, Poland
New MVP feedback
Jun
Engaging students in Portugal
MVP improvements implemented
Notes: These are some of detailed milestones agreed upon in WP7 for upcoming months.
By June, we want to finalise 2nd cycle of MVP improvements.

## Slide 3: Pilot Estimations
Pilot Country | Until now | Until June
Greece | 80 engaged +200 invited | +300 invited
Hungary |  | 40 engaged more others invited
Italy | 500 invited | 100 engaged
Lithuania | 90 engaged | +60 engaged 400 invited
Poland |  | 80 engaged
Portugal |  | 10 engaged
Spain |  | 1+7 engaged 10+ others invited

## Slide 4: Pilot Estimations
Year 2 – 80 schools
Joined in 2019 until now – +90 schools (Lithuania, Greece)
Planned to join by June (overall) – 298 new schools (468 in total)
Invited by June – 1480

## Slide 5: Minimum Viable Product
Q1-Q2 2019 – The second phase for collecting MVP suggestions
  Collecting new suggestions from teachers and students in pilots
  Already have some new suggestions on user experience
  Some feedback to be reported at the project review in March
  More improvements to be implemented and reported by June

## Slide 6: Quality Assurance
Testing activities recently launched for:
  The upgrades of Moodle
  The upgrades of CERNBox
  Poddium (PR) available as standalone tool
  EduOER Android App
Resources to join:
  https://trello.com/b/0G3CLzGx/qa-testing-tool-workflow
  https://wiki.geant.org/display/UP2U/Issue+tracking