## Slide 1: 5th Up2U GA Feedback and Outcomes
Project Coordination Team
5th Up2U General Assembly, Poznan, Poland

## Slide 2: GDPR update
KWS integration
  Top level integration (SSO)
  Push consent collection to all tools
  Minimise data loss
Interim solutions
  Gather consent on school level (e.g. Greek pilot)
  Latest version of Moodle (done, only covers Moodle tools)
More follow up actions identified during Break out sessions

## Slide 3: TF Engaging community update
Define ‘Learning community’ -> what/who is our target
Target teaching/learning communities on social media (FB, a.o.)
Forum for Up2U teachers on up2univerisity.eu?
Notes: WPs 7 and 8 will present later today during designated sessions

## Slide 4: TF Engaging community update
2 levels of engagement next steps:
National level
  Describe processes, implementation, outcomes
  Michal, Gytis, Dimitris, Nadia
  Timeline: 3 weeks from today -> create plan, framework and process. After -> roll out
International level
  Describe processes, implementation, outcomes
  Mary, Gyongyi, Stefano, Eli, Antonio
  Timeline: arrange meeting before the Webinar (2 weeks)
Notes: WPs 7 and 8 will present later today during designated sessions

## Slide 5: TF Uniformed content & pilot activities update
Scope: create categorised courses that are reusable
  Internal -> existing pilots (national languages)
  External -> open content for new users
  Tutorial for teachers: how to use this content
Definition of courses
  What could be considered as a uniform course?
Move courses from learn.test to learn.up2university
  Clean up test courses
  ACTION: National pilot coordinators to inform Allan which courses can be deleted

## Slide 6: Stabilized SSO and other technical constraints discussion
12 issues raised
Reinforce the usage of GitHub
What implications will GDPR/consent collection have on existing users
ACTION: PCT to categorise issues and discuss with relevant partners

## Slide 7: Pilot updates
What makes one pilot implication model more successful than others?
  Badges and certificates
  High quality content
  Using the platform for other purposes: contests, workshops, one-off events
Analysis missing: why don’t teachers complete the CPD cycle?
  During Module 1
  Before including students

## Slide 8: Sustainability
2 main models identified:
Centralised
Decentralised
2 potential models:
CS3MESH4EOSC
University-as-a-Hub
Notes and actions can be found here: https://docs.google.com/document/d/1HN2aPo7PAlJCdhAv0YczfUh2Fh2fASw8iFG0JY8bNuM/edit#

## Slide 9: Pedagogy roadmap
D5.5 outline
Competencies
  Moodle Competency Framework
Survey plugin
Follow up after WP5-WP7 meeting in Rome

## Slide 10: Break out sessions
Fruitful discussions
Clear outcomes (or at least for some!)
Next steps can be found in the slides