## Slide 1: UP2U WP8 Sustainability and Exploitation of Results

## Slide 2: Status of Deliverables
Deliverables | Topic | Status
D8.1 | Analysis of Up2U Ecosystem and Existing Business Models | Accepted
D8.2 | Draft Plan for Sustainability and Exploitation | Accepted
D8.3 | Up2U Business Models | Approved
D8.4 | Final Report on Up2U Sustainability and Exploitation | M39 (May 2020)

## Slide 3: Tasks Update
Task 8.1 – Sustainability and business models (PSNC)
Efforts will focus on implementing these business models in an effective, efficient and consistent manner, as well as on providing effective competitive analyses for achieving a sustainable strategy after the project’s lifetime.
Task 8.2 – Ecosystem Analysis (GWDG)
The task will continue to focus on competitive solutions and the advantages of Up2U’s solution by comparison as part of the ecosystem analysis.

## Slide 4: Tasks Update
Task 8.3 – Industry Engagement (TELTEK)
Companies that may be willing to provide Infrastructure as a Service (IaaS) and that can also offer cloud services to the project, with a focus especially on extender ownCloud compatible storage.
Contact publishers of digital textbooks that can provide commercial educational content to the platform.
Contact Microsoft (Spain branch) or a Microsoft partner to engage as an Office 365 provider for the Up2U platform.
Furthermore, the task will focus on implementing NREN and Up2U tools for school business models and engage local NRENs or commercial providers (for countries where the local NREN is not interested in engaging with the project).
Task 8.4 – New Schools (GARR)
Activities addressed to new schools to fully exploit the benefits of the project will be continued in the last year of the project. Schools are the main target for the proposed business models the project will focus on (NREN services for schools, Up2U Tools for Schools and Third-Party Tool Integration).

## Slide 5: New KPI
Two KPIs were defined in the DoW:
1. Number of Business Models identified and evaluated – 10 required.
5 have already been evaluated and 2 others identified, reported in D8.3.
2. Business actors willing to engage on commercial basis – 5 required.
4 business actors are willing to engage, reported in D8.3.
- Sustainability strategy - Task. 8.1
- Analysis of competitive solutions and our unique selling points - Task 8.2
- Extending the community of schools interested in the Up2U platform - Task 8.4