## Slide 1: WP1 Update
Gyöngyi Horváth
Webinar #4 13/06/2019

## Slide 2: Past - Work done
Up2U Workplan revision
General Assembly
Financial report
  Q8 done
  Q9 – urgently needed to be finalised
Notes: Up2U workplan revision from all WP leaders and the PCT took most the effort which has been made during the last two months as the planning involved agreeing on requesting extension of the project for the purpose of reaching the key KPIs and the key objectives of the project. The extension is planned for 4 months with the 5th month as the reporting time indicated. In the meantime the key focus will be on getting more pilots to the project.
General Assembly is planned for 10-11 September in Poznan, Poland. Logistics arrangements has started and agenda preparations have been made.
Financial report – Past period:
  Q8 is finalized
  Q9 reporting:
    Submitted by:
    Missing from:
      GRNET
      ISEP
      IUCC
      OwnCloud
      GWDG

## Slide 3: Future - Ongoing/Planned work
Submit request to the EC for extension
Revising deadlines
Finance
Monthly reporting:
  Overall project
  Pilots
  Communication
  Finance
Notes: If the Up2U revised workplan is approved by the reviewers we need to submit an official request to the EC for the extension proposed. This also requires all deadlines to be amended and all relevant team members to be informed (GEANT Technical Authors…etc).
Once again, once the workplan approved, the finance / person effort needs to be amended based on the proposal. Relevant team members will need to submit change requests, person months needs to be amended from all WPs and also from the finance team.
Monthly project reporting should now be back to normal: monthly webinar to be the base for the reports.