## Slide 1
Stefan Winter
Roadmap
eduroam-as-a-service
Last update: 02 nov 2016
Task Leader GN4-2 JRA3-T4
R&D Engineer, RESTENA Foundation

## Slide 2: Overall product development timeline
Overall system design specified – DONE
Implement first prototype – ONGOING
finalize first prototype for the service – Dec 2016 [COMMITED]
launch pilot for the service – Jan 2017 [COMMITED]
-> functional except credential revocation; preliminary UI; see “Pilot Features”
stop the pilot – May 2017 [PLANNED]
eaas beta version – June 2017 [PLANNED]
-> fully functional, near-final UIs; see “Beta Features”
eaas v1.0 – July 2017 [PLANNED]
documentation and acceptance testing – Sep 2017 [POSSIBILITY]
service launch and handover to production – Oct 2017 [POSSIBILITY]

## Slide 3: Pilot Features (1) – JAN 2017
NRO Administrator interface
  Functionality: FINISHED
    NRO can mark a future IdP as eligible for the service
    Invitations for IdP management are sent to the designated IdP administrators
    Issued invitation tokens can be consumed, IdP created and activated
    Designated IdP admin can use IdP user provisioning interface, below
  User Interface: PRELIMINARY
    will need polishing
IdP user provisioning interface
  Functionality: 80% FINISHED
    IdP admin can log into the system
    Can add and remove users
    Can issue new vouchers
    Can NOT revoke issued credentials yet (button exists, without function)
  User Interface: PRELIMINARY
    Will need polishing

## Slide 4: Pilot Features (2) – JAN 2017
End-user interface
  Functionality: 90% FINISHED
    Provisioning
      Able to consume vouchers
      Detect operating system of end user
      Creates customised installer based on voucher validity and operating system
      Possible limitation: installers not yet ready for some operating systems
    Status Page
      Able to inform user about status of his account, based on voucher code or client cert
      Possible limitation: … „based on client cert“ possibly not functional yet
  User Interface: PRELIMINARY
    will need polishing
Certification Authority for client certificates
  50% FINISHED
    PHP-based stub implementation of CA signatures
    Unable to handle revocation

## Slide 5: Pilot Features (3) – JAN 2017
RADIUS server implementation
  IdP part (account validation) – 90% FINISHED
    EAP-TLS termination point for @*.hosted.eduroam.org
    Presents per-NRO server certificate
    Validates client certificates against root and (stub) intermediate
    Does not verify revocation status with OCSP yet
  SP part (on-site proxy) – 50% FINISHED
    Basic functionality available
    Recommended features as per eduroam Service Definition may not be fully implemented yet
OCSP server
  Not in place yet due to missing revocation functionality

## Slide 6: Beta Features (1) – JUNE 2017
NRO Administrator interface
  Functionality: FINISHED
    NRO can mark a future IdP as eligible for the service
    Invitations for IdP management are sent to the designated IdP administrators
    Issued invitation tokens can be consumed, IdP created and activated
    Designated IdP admin can use IdP user provisioning interface, below
  User Interface: FINISHED
    Following input and consensus from pilot testers
IdP user provisioning interface
  Functionality: FINISHED
    IdP admin can log into the system
    Can add and remove users
    Can issue new vouchers
    Revocation working (button functional)
  User Interface: FINISHED
    Following input and consensus from pilot testers

## Slide 7: Beta Features (2) – JUNE 2017
End-user interface
  Functionality: FINISHED
    Provisioning
      Able to consume vouchers
      Detect operating system of end user
      Creates customised installer based on voucher validity and operating system
      installers available for all supported operating systems (pending OS bugs preventing actual use)
    Status Page
      Able to inform user about status of his account, based on voucher code or client cert
      Possible limitation: … „based on client cert“ possibly not functional yet
  User Interface: FINISHED
    Following input and consensus from pilot testers
Certification Authority for client certificates
  FINISHED
    CA operation moved to dedicated VM with HSM
    Regulary issues OCSP revocation status responses
    Sends OCSP status responses to OCSP server for public consumtion

## Slide 8: Beta Features (3) – JUNE 2017
RADIUS server implementation
  IdP part (account validation) – FINISHED
    EAP-TLS termination point for @*.hosted.eduroam.org
    Presents per-NRO server certificate
    Validates client certificates against root and HSM-based intermediate
    Checks revocation status against OCSP server
  SP part (on-site proxy) – FINISHED
    Basic functionality available
    Recommended features as per eduroam Service Definition implemented
OCSP server FINISHED
  Two worker VMs and load-balancing front-end deployed
  simplistic web server to hand out OCSP responses (low load)

## Slide 9
Stefan Winter <stefan.winter@restena.lu>